## Lists (hidden)
CUST-001 - ASMAC | Draft | Entered | Entered
CUST-002 - Chennai Metro Water and Sewerage Board | Entered | In Progress | In Progress
CUST-004 - Inspirisys | In Progress | Pending | Pending
CUST-003 - Yaanar Tech | On Hold | On Hold | Awaiting Approval
| Completed | Completed | Awaiting User Input
| Cancelled | Cancelled | Testing
Completed
Cancelled

## Project
Project Name * | Customer * | Start Date * | End Date * | Extension Date | Status
Digistorii | CUST-003 - Yaanar Tech | 2026-04-01 | 2026-12-31 |  | In Progress

## Scope
Project Name * | Scope Name * | Description | Start Date * | End Date * | Status
Digistorii | POS | Back-office and point-of-sale: masters, product and pricing, sales billing, purchase, inventory and stock, returns, validations and dashboard. | 2026-04-01 | 2026-10-31 | In Progress
Digistorii | Tenant Creation | SaaS layer: onboarding, plans, subscription and billing, users and roles, authentication, deployment and tenant security. | 2026-04-24 | 2026-11-20 | In Progress
Digistorii | E-Commerce | Online storefront: settings, theme and template, catalogue, cart, customer account, checkout, payments, orders, delivery, reports and go-live. | 2026-08-05 | 2026-12-31 | In Progress

## Milestone
Project Name * | Scope Name * | Milestone Name * | Start Date * | End Date * | Status
Digistorii | POS | Product and pricing masters | 2026-04-01 | 2026-04-07 | Completed
Digistorii | POS | Sales billing | 2026-04-06 | 2026-08-21 | Completed
Digistorii | POS | Inventory, stock and returns | 2026-04-17 | 2026-10-31 | In Progress
Digistorii | POS | Purchase and procurement | 2026-04-24 | 2026-08-13 | Completed
Digistorii | POS | Validation, UX and reports | 2026-06-30 | 2026-08-24 | Completed
Digistorii | Tenant Creation | Onboarding workflow | 2026-05-06 | 2026-08-18 | Completed
Digistorii | Tenant Creation | Plans, subscription and billing | 2026-06-26 | 2026-07-31 | Completed
Digistorii | Tenant Creation | Users, roles and access | 2026-06-15 | 2026-08-10 | Completed
Digistorii | Tenant Creation | Deployment and environments | 2026-04-24 | 2026-08-06 | Completed
Digistorii | Tenant Creation | Tenant security hardening | 2026-10-23 | 2026-11-20 | In Progress
Digistorii | E-Commerce | Ecom foundation and settings | 2026-08-05 | 2026-09-10 | Completed
Digistorii | E-Commerce | Storefront template and theme | 2026-08-25 | 2026-11-27 | In Progress
Digistorii | E-Commerce | Catalogue and product pages | 2026-08-31 | 2026-11-27 | In Progress
Digistorii | E-Commerce | Cart, account and checkout | 2026-09-01 | 2026-12-11 | In Progress
Digistorii | E-Commerce | Payments and invoicing | 2026-09-08 | 2026-12-23 | In Progress
Digistorii | E-Commerce | Orders and stock integration | 2026-09-07 | 2026-12-11 | In Progress
Digistorii | E-Commerce | Delivery and logistics | 2026-09-07 | 2026-12-23 | In Progress
Digistorii | E-Commerce | Reports, testing and go-live | 2026-11-27 | 2026-12-31 | Entered

## Task
Project Name * | Scope Name * | Milestone Name * | Task Name * | Start Date * | Due Date * | Status
Digistorii | POS | Product and pricing masters | Module exploration and data-flow setup | 2026-04-01 | 2026-04-01 | Completed
Digistorii | POS | Product and pricing masters | Product master and UI | 2026-04-02 | 2026-04-02 | Completed
Digistorii | POS | Product and pricing masters | Product lookup logic and backend API | 2026-04-03 | 2026-04-03 | Completed
Digistorii | POS | Product and pricing masters | Product fetch performance and edge cases | 2026-04-04 | 2026-04-04 | Completed
Digistorii | POS | Product and pricing masters | Pricing UI (allocation, Excel template) | 2026-04-06 | 2026-04-07 | Completed
Digistorii | POS | Product and pricing masters | Discount scheme setup | 2026-04-07 | 2026-04-07 | Completed
Digistorii | POS | Sales billing | Sales billing UI, discount and price fetch | 2026-04-06 | 2026-04-10 | Completed
Digistorii | POS | Sales billing | Sales billing with warehouse stock deduction | 2026-06-02 | 2026-06-02 | Completed
Digistorii | POS | Sales billing | Product lookup restriction in sales | 2026-06-01 | 2026-07-02 | Completed
Digistorii | POS | Sales billing | Barcode and product scanning | 2026-06-06 | 2026-06-10 | Completed
Digistorii | POS | Sales billing | Tax id, payment mode, warehouse and location fetch | 2026-06-12 | 2026-06-12 | Completed
Digistorii | POS | Sales billing | Print address and payment breakdown | 2026-07-21 | 2026-07-24 | Completed
Digistorii | POS | Sales billing | Keyboard shortcuts for billing | 2026-07-24 | 2026-07-24 | Completed
Digistorii | POS | Sales billing | Correct tenant address in Bill To / Ship To | 2026-08-19 | 2026-08-19 | Completed
Digistorii | POS | Sales billing | Accurate paid and return amount status | 2026-08-20 | 2026-08-20 | Completed
Digistorii | POS | Sales billing | Hold bill feature | 2026-08-21 | 2026-08-21 | Completed
Digistorii | POS | Inventory, stock and returns | Inventory submodule testing (forms, CRUD, flow) | 2026-04-17 | 2026-04-22 | Completed
Digistorii | POS | Inventory, stock and returns | Image master and product form testing and fixes | 2026-04-28 | 2026-04-30 | Completed
Digistorii | POS | Inventory, stock and returns | Stock adjustment | 2026-08-01 | 2026-08-05 | Completed
Digistorii | POS | Inventory, stock and returns | Sales return | 2026-08-01 | 2026-08-01 | Completed
Digistorii | POS | Inventory, stock and returns | Sales exchange | 2026-07-31 | 2026-10-31 | In Progress
Digistorii | POS | Inventory, stock and returns | Purchase return | 2026-08-03 | 2026-08-03 | Completed
Digistorii | POS | Inventory, stock and returns | Low-stock and back-order notifications | 2026-08-22 | 2026-08-22 | Completed
Digistorii | POS | Purchase and procurement | Purchase form and approval flow testing | 2026-04-24 | 2026-04-24 | Completed
Digistorii | POS | Purchase and procurement | Supplier form testing | 2026-04-27 | 2026-04-27 | Completed
Digistorii | POS | Purchase and procurement | Purchase order add product bug fix | 2026-08-03 | 2026-08-04 | Completed
Digistorii | POS | Purchase and procurement | PO pricing in pricing form | 2026-07-27 | 2026-07-27 | Completed
Digistorii | POS | Purchase and procurement | Bypass duplicate OPS for same variants | 2026-08-11 | 2026-08-11 | Completed
Digistorii | POS | Purchase and procurement | Reorder PO form table columns | 2026-08-13 | 2026-08-13 | Completed
Digistorii | POS | Validation, UX and reports | Added fields: gender, fitting, colours | 2026-07-07 | 2026-07-08 | Completed
Digistorii | POS | Validation, UX and reports | Field validation function, including address fields | 2026-07-09 | 2026-07-16 | Completed
Digistorii | POS | Validation, UX and reports | Alert-to-toast, Excel dropdowns, payment mode tweaks | 2026-07-17 | 2026-07-18 | Completed
Digistorii | POS | Validation, UX and reports | Field info messages and country auto-populate | 2026-07-20 | 2026-07-20 | Completed
Digistorii | POS | Validation, UX and reports | Sales analytics graph and chart debug | 2026-08-06 | 2026-08-24 | Completed
Digistorii | POS | Validation, UX and reports | Functionality test document | 2026-06-30 | 2026-06-30 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Pricing page flow and plan card selection | 2026-05-06 | 2026-05-08 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Onboarding steps design | 2026-05-25 | 2026-05-29 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Onboarding steps edit and changes | 2026-06-15 | 2026-06-23 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Onboarding form validation | 2026-07-15 | 2026-07-16 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Split onboarding workflow steps | 2026-08-10 | 2026-08-11 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Show previous fill-ups as read-only | 2026-08-12 | 2026-08-12 | Completed
Digistorii | Tenant Creation | Onboarding workflow | Post-payment welcome and business setup redirect | 2026-08-18 | 2026-08-18 | Completed
Digistorii | Tenant Creation | Plans, subscription and billing | Plan changes including Ecom access | 2026-06-26 | 2026-06-26 | Completed
Digistorii | Tenant Creation | Plans, subscription and billing | Add more users by paying (seat purchase) | 2026-07-30 | 2026-07-30 | Completed
Digistorii | Tenant Creation | Plans, subscription and billing | Subscription renewal with email warning | 2026-07-31 | 2026-07-31 | Completed
Digistorii | Tenant Creation | Users, roles and access | User responsibilities creation | 2026-06-15 | 2026-06-15 | Completed
Digistorii | Tenant Creation | Users, roles and access | Workspace user panel; responsibilities moved to admin | 2026-06-26 | 2026-06-29 | Completed
Digistorii | Tenant Creation | Users, roles and access | Admin validation | 2026-07-21 | 2026-07-21 | Completed
Digistorii | Tenant Creation | Users, roles and access | Forgot and reset password | 2026-07-20 | 2026-07-23 | Completed
Digistorii | Tenant Creation | Users, roles and access | Company name instead of slug in sidebar and login | 2026-07-27 | 2026-07-27 | Completed
Digistorii | Tenant Creation | Users, roles and access | Page navigation and login-interchange restrictions | 2026-07-30 | 2026-07-30 | Completed
Digistorii | Tenant Creation | Users, roles and access | Responsibility column in admin user table | 2026-08-10 | 2026-08-10 | Completed
Digistorii | Tenant Creation | Deployment and environments | GitHub org connection and pull requests | 2026-04-24 | 2026-04-27 | Completed
Digistorii | Tenant Creation | Deployment and environments | Hostinger deployment for demo | 2026-05-19 | 2026-05-21 | Completed
Digistorii | Tenant Creation | Deployment and environments | Vercel dev deployment and build fixes | 2026-06-24 | 2026-06-25 | Completed
Digistorii | Tenant Creation | Deployment and environments | SMTP email setup | 2026-07-29 | 2026-07-29 | Completed
Digistorii | Tenant Creation | Deployment and environments | Separate Ecom and POS code and Vercel projects | 2026-08-06 | 2026-08-06 | Completed
Digistorii | Tenant Creation | Tenant security hardening | Signed sessions | 2026-10-23 | 2026-10-30 | In Progress
Digistorii | Tenant Creation | Tenant security hardening | Login check on every back-office API | 2026-10-23 | 2026-11-06 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Tenant taken from server, not from request headers | 2026-10-23 | 2026-11-06 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Remove env file from git and rotate all keys | 2026-10-23 | 2026-10-30 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Set ENCRYPTION_KEY and merge gateway config into encrypted store | 2026-10-23 | 2026-10-30 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Block expired tenants from storefront and checkout | 2026-10-30 | 2026-11-13 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Authenticate Socket.IO and restrict CORS | 2026-10-30 | 2026-11-13 | Entered
Digistorii | Tenant Creation | Tenant security hardening | Tests: cross-tenant access and IDOR | 2026-11-06 | 2026-11-20 | Entered
Digistorii | E-Commerce | Ecom foundation and settings | Ecom modules started and storefront settings | 2026-08-05 | 2026-08-07 | Completed
Digistorii | E-Commerce | Ecom foundation and settings | API spike for product fetching | 2026-08-07 | 2026-08-07 | Completed
Digistorii | E-Commerce | Ecom foundation and settings | Merge Ecom with latest POS code | 2026-08-25 | 2026-08-25 | Completed
Digistorii | E-Commerce | Ecom foundation and settings | Ecom settings (payment mode, gateway, courier, shipping) | 2026-08-07 | 2026-09-10 | Completed
Digistorii | E-Commerce | Storefront template and theme | Template refactor and live | 2026-08-25 | 2026-08-26 | Completed
Digistorii | E-Commerce | Storefront template and theme | Template renders company products | 2026-08-27 | 2026-08-27 | Completed
Digistorii | E-Commerce | Storefront template and theme | Theme setup per user allocation | 2026-08-27 | 2026-08-27 | Completed
Digistorii | E-Commerce | Storefront template and theme | Font, category and image fixes on Vercel | 2026-08-28 | 2026-08-28 | Completed
Digistorii | E-Commerce | Storefront template and theme | Home page editing (new arrivals, offers, carousel) | 2026-09-03 | 2026-09-03 | Completed
Digistorii | E-Commerce | Storefront template and theme | Mobile responsiveness review | 2026-10-23 | 2026-11-15 | In Progress
Digistorii | E-Commerce | Storefront template and theme | SEO tags per page | 2026-10-30 | 2026-11-13 | Entered
Digistorii | E-Commerce | Storefront template and theme | Policy pages (terms, privacy, returns) | 2026-10-30 | 2026-11-13 | Entered
Digistorii | E-Commerce | Storefront template and theme | Banner and promo scheduling | 2026-11-13 | 2026-11-27 | Entered
Digistorii | E-Commerce | Catalogue and product pages | Product detail page with variant allocation | 2026-08-31 | 2026-08-31 | Completed
Digistorii | E-Commerce | Catalogue and product pages | Category navigation, quick view, image zoom | 2026-09-01 | 2026-09-01 | Completed
Digistorii | E-Commerce | Catalogue and product pages | Discounted price with badges | 2026-09-02 | 2026-09-02 | Completed
Digistorii | E-Commerce | Catalogue and product pages | Price fetch with both discounts; expired pricing | 2026-09-05 | 2026-09-05 | Completed
Digistorii | E-Commerce | Catalogue and product pages | Ecom override amount bug | 2026-09-07 | 2026-09-07 | Completed
Digistorii | E-Commerce | Catalogue and product pages | Filters, sorting, pagination | 2026-10-23 | 2026-11-15 | In Progress
Digistorii | E-Commerce | Catalogue and product pages | Out-of-stock display and back-in-stock handling | 2026-11-06 | 2026-11-20 | Entered
Digistorii | E-Commerce | Catalogue and product pages | Related products | 2026-11-13 | 2026-11-27 | Entered
Digistorii | E-Commerce | Cart, account and checkout | Wishlist and cart | 2026-09-01 | 2026-09-01 | Completed
Digistorii | E-Commerce | Cart, account and checkout | Customer account creation and sign-in | 2026-09-02 | 2026-09-02 | Completed
Digistorii | E-Commerce | Cart, account and checkout | Saved addresses (multiple) | 2026-09-09 | 2026-09-09 | Completed
Digistorii | E-Commerce | Cart, account and checkout | Checkout payment | 2026-09-08 | 2026-09-09 | Completed
Digistorii | E-Commerce | Cart, account and checkout | Coupon, shipping fee and free-delivery threshold | 2026-09-09 | 2026-09-10 | Completed
Digistorii | E-Commerce | Cart, account and checkout | Address selection and ownership validation | 2026-10-23 | 2026-11-05 | In Progress
Digistorii | E-Commerce | Cart, account and checkout | Account page: order history and reorder | 2026-10-23 | 2026-11-15 | In Progress
Digistorii | E-Commerce | Cart, account and checkout | Checkout uses logged-in customer, not request value | 2026-10-23 | 2026-11-06 | Entered
Digistorii | E-Commerce | Cart, account and checkout | Pincode serviceability check at checkout | 2026-10-30 | 2026-11-13 | Entered
Digistorii | E-Commerce | Cart, account and checkout | Coupon usage limits | 2026-11-06 | 2026-11-20 | Entered
Digistorii | E-Commerce | Cart, account and checkout | OTP login through SMS provider (remove demo OTP) | 2026-10-30 | 2026-11-13 | Entered
Digistorii | E-Commerce | Cart, account and checkout | Abandoned-cart reminders | 2026-11-27 | 2026-12-11 | Entered
Digistorii | E-Commerce | Payments and invoicing | Razorpay order, signature verify and webhook | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Payments and invoicing | Cash on delivery | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Payments and invoicing | Refund on cancel of paid order | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Payments and invoicing | Failed-payment retry | 2026-11-13 | 2026-11-27 | Entered
Digistorii | E-Commerce | Payments and invoicing | Partial refunds for returns | 2026-11-27 | 2026-12-11 | Entered
Digistorii | E-Commerce | Payments and invoicing | Invoice PDF with GST, emailed to customer | 2026-12-09 | 2026-12-23 | Entered
Digistorii | E-Commerce | Orders and stock integration | Order state machine (order, payment, delivery) | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Orders and stock integration | Status history log | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Orders and stock integration | Admin actions: confirm, allocate, pack, ship, deliver, cancel | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Orders and stock integration | Admin orders page (basic) | 2026-09-07 | 2026-11-30 | In Progress
Digistorii | E-Commerce | Orders and stock integration | Post online sales to stock ledger | 2026-10-23 | 2026-11-06 | Entered
Digistorii | E-Commerce | Orders and stock integration | Release stock when a confirmed order is cancelled | 2026-10-23 | 2026-11-06 | Entered
Digistorii | E-Commerce | Orders and stock integration | Order filters and search | 2026-11-06 | 2026-11-20 | Entered
Digistorii | E-Commerce | Orders and stock integration | Order confirmation by email and SMS | 2026-11-20 | 2026-12-04 | Entered
Digistorii | E-Commerce | Orders and stock integration | Customer cancellation window | 2026-11-27 | 2026-12-11 | Entered
Digistorii | E-Commerce | Delivery and logistics | Courier and orders UI | 2026-09-07 | 2026-09-07 | Completed
Digistorii | E-Commerce | Delivery and logistics | Delivery webhook with signature check | 2026-09-08 | 2026-09-08 | Completed
Digistorii | E-Commerce | Delivery and logistics | Outbound courier API to create shipment and AWB | 2026-11-13 | 2026-11-27 | Entered
Digistorii | E-Commerce | Delivery and logistics | Customer tracking page | 2026-11-27 | 2026-12-11 | Entered
Digistorii | E-Commerce | Delivery and logistics | Returns and exchange pickup | 2026-12-09 | 2026-12-23 | Entered
Digistorii | E-Commerce | Reports, testing and go-live | Online sales and orders-by-status reports | 2026-11-27 | 2026-12-11 | Entered
Digistorii | E-Commerce | Reports, testing and go-live | End-to-end tests: prepaid, COD, cancel, refund | 2026-12-04 | 2026-12-18 | Entered
Digistorii | E-Commerce | Reports, testing and go-live | Rate limiting, input validation, monitoring | 2026-12-09 | 2026-12-23 | Entered
Digistorii | E-Commerce | Reports, testing and go-live | Backups, staging and go-live checklist | 2026-12-17 | 2026-12-31 | Entered